MILESTONE COMPLETION SCHEDULE

Project title:

The completion SCHEDULE of WORK is XX months from Effective Date. Milestone Completion Schedule shall be filled In line with Project Overall Schedule.

| Mile-stone No | Milestone Title | Weight % | No. of Months from EFFECTIVE DATE | Detail Description / Remarks |
| --- | --- | --- | --- | --- |
| A | ENGINEERING |  |  |  |
| a. | General |  |  |  |
|  | Milestone #1 | Please fill |  |  |
|  | Milestone #1. | Please fill |  |  |
| b. | Buildings | Please fill |  |  |
|  | Issue Architectural & Foundation Structural Drawings for Building.xxxxxx (IFC). | Please fill |  |  |
|  | Issue Kitchen Equipment Layout for Building xxxxxx for Client Approval. | Please fill |  |  |
|  | Issue Architectural & Structural Drawings for Building xxx extensions (IFC). | Please fill |  |  |
|  | Issue of 3D perspective Drawings for all Buildings. | Please fill |  |  |
|  | Issue Finishing Schedules & Shop Drawings for all Building for Approval. | Please fill |  |  |
|  | Complete Heat Load Calculation and Submit HVAC Key Drawings and Layouts for Approval. | Please fill |  |  |
|  | Complete Electrical Load Calculation and Submit SLD, Equipment Rating and Cable schedules for approval. | Please fill |  |  |
|  | Complete issue of Electrical & Instrumentation drawings for all Buildings (IFC). | Please fill |  |  |
|  | Complete Detailed Design and Issue Drawings for CCTV/PA & Telecom Systems for Approval. | Please fill |  |  |
|  | Complete Detailed Design and Issue Drawings for Audio / Video system at Building xxxxx for Approval. | Please fill |  |  |
|  | Complete Detailed design for Lab. Equipment & Piping and Issue all Drawings (IFC) | Please fill |  |  |
| c. | External & Common Facilities | Please fill |  |  |
|  | Complete Stress Analysis and submit Drawings for Fire Water System (IFC) | Please fill |  |  |
|  | Issue all civil drawings for the Access Road to Building (IFC). | Please fill |  |  |
|  | Issue External Co-ordinated Service Drawings for all services (IFC). | Please fill |  |  |
|  | Complete Design & Issue Architectural / Structural Drawings for Car park shed, Roads, Hard and Soft Landscaping (IFC). | Please fill |  |  |
| B. | PROCUREMENT (Ordering & Delivery) |  |  |  |
|  | Finalize Award of Subcontract for EMI / Kitchen / Lab Equipment Installation works. | Please fill |  |  |
|  | Finalize Award of Subcontract for furniture supply / installation. | Please fill |  |  |
|  | Issue Purchase Order for all HVAC Equipment. | Please fill |  |  |
|  | Issue Purchase Order for Electrical / Instrumentation /Telecommunication materials. | Please fill |  |  |
|  | Issue Purchase Order for Interior / Exterior Finishes and Decoration materials. | Please fill |  |  |
|  | Issue Purchase Order for Kitchen Equipment. | Please fill |  |  |
|  | Issue Purchase Order for Laboratory Equipment. | Please fill |  |  |
|  | Issue Purchase Order for finishes, Special lighting and AV System at Auditorium | Please fill |  |  |
|  | Issue Purchase Order for Furniture. | Please fill |  |  |
|  | Receive all Long Lead HVAC Equipment at site. | Please fill |  |  |
|  | Receive all Long Lead Electrical / Instrumentation materials at site. | Please fill |  |  |
|  | Receive all for Interior, Exterior Finishes and Decoration materials at site. | Please fill |  |  |
|  | Receive all Telecommunication material at site. | Please fill |  |  |
|  | Receive all Kitchen Equipment at site. | Please fill |  |  |
|  | Receive all Laboratory Equipment & piping material at site. | Please fill |  |  |
|  | Receive all Furniture at site. | Please fill |  |  |
| C. | CONSTRUCTION & COMMISSIONING |  |  |  |
| a. | General |  |  |  |
|  | Complete relocation of existing services. | Please fill |  |  |
| b. | Building-1 | Please fill |  |  |
|  | Complete Building Sub-Structure works up to grade beam and backfilling. | Please fill |  |  |
|  | Complete all Super-Structural concreting works. | Please fill |  |  |
|  | Complete Civil Initial finishing works. | Please fill |  |  |
|  | Complete all HVAC & EMI First fix installation works. | Please fill |  |  |
|  | Complete Civil final finishing, Furniture installation & AV system installation at Auditorium & Canteen. | Please fill |  |  |
|  | Complete works at Outdoor area with soft & hard landscaped areas. | Please fill |  |  |
| c. | Building – Extension | Please fill |  |  |
|  | Complete Building Sub-Structure works up to grade beam and backfilling. | Please fill |  |  |
|  | Complete all Super-Structural concreting works. | Please fill |  |  |
|  | Complete all Finishing, HVAC, Electrical, & Instrumentation Installation works and Handover | Please fill |  |  |
| d. | Common Facilities – Substation Modification & External Works | Please fill |  |  |
|  | Complete Panel Modification (electrical) at Substation. | Please fill |  |  |
|  | Complete installation of covered car parks at all locations. | Please fill |  |  |
|  | Complete installation of External Underground Services including backfilling. | Please fill |  |  |
|  | Complete Pavement & access road | Please fill |  |  |
|  | Complete all Landscaping and Irrigation | Please fill |  |  |
| g. | Commissioning Works | Please fill |  |  |
|  | Complete Electrical power tie-in at Substation#xxxx & Energization. | Please fill | 16 M |  |
|  | Complete Commissioning of HVAC | Please fill |  |  |
|  | Complete Instrumentation tie-in works for all services. | Please fill |  |  |
|  | Complete Commissioning and Handover Building –xxxxx | Please fill | 21 M |  |
|  | Complete Commissioning all External Services & other Buildings and Handover. | Please fill | 23 M |  |
|  | Complete As-built documentations, Submit Project Close-out reports. | Please fill |  |  |
|  | Complete Construction and Commissioning of all other Buildings & External Services and achieve Completion certificate (Note 2) | Please fill | 24 M |  |
|  | TOTAL | ATTACHMENT– 2 PAGE 1 OF 2 (Section-3, Part-1) 100% |  |  |

NOTES:-

Note 2 : Indicates LD Milestones.